## Sheet1
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  |  | 20 make timeline write DESIGN read XICE | 21 write DESIGN read personalServer find papers | 22
23 write DESIGN find papers read | 24 implement hiding + size constraints (maxZ?) write RELWORK | 25 write RELWORK 15:00 Juan meeting read | 26 | 27 deadline DESIGN prepare EVAL read | 28 | 29 prepare EVAL write INTRO
30 prepare EVAL test run EVAL | 31 finalize EVAL write RELWORK | 1 write RELWORK rewrite DESIGN | 2 | 3 deadline RELWORK + INTRO | 4 write SYSTEM | 5 finalize EVAL
6 run EVAL write SYSTEM | 7 run EVAL write SYSTEM | 8 write SYSTEM rewrite RELWORK + INTRO | 9 | 10 deadline SYSTEM analyze EVAL | 11 make VIDEO | 12 make VIDEO
13 analyze EVAL write EVAL | 14 deadline EVAL | 15 write THEORY | 16 | 17 deadline THEORY | 18 write DISCUSSION + CCL | 19 deadline DISCUSSION + CCL
20 rewrite SYSTEM | 21 rewrite EVAL | 22 rewrite THEORY | 23 | 24 rewrite DISCUSSION + CCL | 25 finalize video | rewrite
27 rewrite | 28 rewrite | 29 print | 1 HAND-IN before 15:00