## Sheet1
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  |  | 20 make timeline write DESIGN read XICE | 21 write DESIGN read find papers | 22
23 write DESIGN find papers read | 24 write DESIGN find papers | 25 find papers write DESIGN 15:00 Juan meeting read | 26 result analysis w. charts (table?) | 27 deadline DESIGN prepare EVAL 13 related work w. AU read | 28 implement hiding + size constraints (maxZ?) | 29 prepare EVAL write INTRO
30 prepare EVAL write intro | 31 finalize EVAL write intro | 1 write intro rewrite DESIGN test run EVAL | 2 | 3 deadline INTRO | 4 finalize EVAL | 5 finalize EVAL rewrite DESIGN
6 run EVAL rewrite DESIGN | 7 run EVAL rewrite INTRO | 8 write RELWORK analyze EVAL | 9 write RELWORK analyze EVAL | 10 deadline RELWORK analyze EVAL | 11 make VIDEO take pictures | 12 make VIDEO
13 write SYSTEM | 14 write SYSTEM | 15 deadline SYSTEM | 16 write EVAL | 17 deadline EVAL | 18 write DISCUSSION + CCL | 19 deadline DISCUSSION + CCL
20 rewrite SYSTEM | 21 rewrite EVAL | 22 rewrite THEORY | 23 | 24 rewrite DISCUSSION + CCL | 25 finalize video | rewrite
27 rewrite | 28 rewrite | 29 print | 1 HAND-IN before 15:00